## Gantt_Projet
Gantt Diagram — Web Project
Step | Task | Responsible | Status | S1 03/09 | S2 10/09 | S3 17/09 | S4 24/09 | S5 01/10 | S6 08/10 | S7 15/10 | S8 22/10 | S9 29/10 | S10 04/11 | S11 12/11 | S12 19/11 | S13 26/11 | S14 03/12 | S15 09/12 | S16 17/12
Concept | Defining the project and entities | Tom & Antonin | Finished
Concept | Planning fonctionalities | Tom | Finished
Concept | ER-diagram and table structure | Antonin | Finished
Database | Complete SQL | Tom | Finished
Database | Creating fake JSON | Antonin | Finished
Starting vue,js | Initializing vue.js | Tom | Finished
Starting vue,js | Creating 3 first pages | Tom | Finished
Starting vue,js | Use-Case and Grantt diagram | Antonin | Finished
Complete Frontend | Frontend | Tom & Antonin | To Do
Complete Frontend | All diagrams for each members | Tom & Antonin | To Do
Server | Initializing server Node.js and connexion with database | Antonin | To Do
Server | Developpement of API and tests with Postman | Tom | To Do
Serveur | Componnents diagram and Classes diagram | Antonin & Tom | To Do
API Integration | Connexion Frontend-Backend | Tom | To Do
API Integration | Autentification implementation | Antonin | To Do
API Integration | Updating UML diagrams | Tom & Antonin | To Do
Final Step | Adding extra business logic | Tom & Antonin | To Do
Final Step | Updating Gantt diagram | Tom & Antonin | To Do